|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Name | Duration | Start | Finish | Predecessors |
| 1 | **Planning** | 13 days | 1/20/16 | 2/6/16 |  |
| 2 | Client searching | 2 days | 1/20/16 | 1/21/16 |  |
| 3 | Client meeting | 2 days | 1/22/16 | 1/23/16 | 2 |
| 4 | Giving project requirements | 1 day | 1/24/16 | 1/24/16 |  |
| 5 | Project planning | 5 days | 1/25/16 | 1/29/16 | 4 |
| 6 | **Analysis** | 4 days | 1/30/16 | 2/2/16 |  |
| 7 | Analysis of requirements | 4 days | 1/30/16 | 2/2/16 |  |
| 8 | Requirements gathering | 4 days | 1/30/16 | 2/2/16 |  |
| 9 | Studying how the project will be execute | 4 days | 1/30/16 | 2/2/16 |  |
| 10 | **Design** | 7 days | 2/4/16 | 2/10/16 |  |
| 11 | System Design | 4 days | 2/7/16 | 2/10/16 | 11 |
| 12 | **Develop** | 47 days | 2/11/16 | 3/28/16 |  |
| 13 | Coding the system | 46 days | 2/11/16 | 3/27/16 | 11,12 |
| 14 | Completion of system | 1 day | 3/28/16 | 3/28/16 | 14 |
| 15 | **Testing** | 5 days | 3/28/16 | 4/1/16 |  |
| 16 | Debugging the system | 4 days | 3/28/16 | 3/31/16 |  |
| 17 | Testing the system | 1 day | 4/1/16 | 4/1/16 |  |
| 18 | **Deployment** | 2 days | 4/8/16 | 4/11/16 |  |
| 19 | Present the system to the client | 1 day | 4/8/16 | 4/8/16 | 15 |
| 20 | Giving the system to the client | 1 day | 4/11/16 | 4/11/16 | 15 |
| 21 | Giving instructions in how to use the system | 1 day | 4/11/16 | 4/11/16 |  |

Activity List